# (NOTE: the header can be removed by double-clicking the header section, right-clicking on the table, and selecting Delete Table. Remove this text when using template.)

# MONITORING PLAN

Study Protocol:

Study Protocol Number:

Study Sponsor Name: Dr. XXX

Research Institute of the McGill University Health Centre

Version 1

dd mmm yyyy

APPROVALS

| Author (CIM, RI, MUHC/Project Manager): XYZ | Signature | Date |
| --- | --- | --- |
| Approval (CIM, RI-MUHC/CRA): XYZ | Signature | Date |
| Approval of Sponsor or Sponsor-Investigator: Dr. XXX | Signature | Date |

| Document History |  |  |
| --- | --- | --- |
| Version | Date | Comments |
| 1.0 | dd mmm yyyy | Draft or Final/Monitoring plan refers to protocol v.#, dd-mm-yyyy. |

Contents

1.	Introduction	4

2.	Overview of the STUDY PROTOCOL/Registry	4

3.	REFERENCES	5

4.	List of ABBREVIATIONS and definitions	5

5.	Monitor training	6

6.	communication	6

6.1	Communication with the Sponsor or Sponsor-Investigator	6

6.2	Communication with the Site	6

7.	Monitoring and site management guidelines	7

7.1	General	7

7.2	Monitoring Visit Frequency	8

7.3	Site Personnel Training	8

7.4	Site Visit Reports	8

8.	Site Visit	9

8.1	Site Initiation Visits (SIV)	9

8.2	Scheduling Site Initiation Visit	10

8.2.1	Tasks to be performed during the Site Initiation Visit	10

8.2.2	Summarizing the Site Initiation Visit	11

8.3	Site Monitoring Visits	11

8.3.1	Scheduling the Site Monitoring Visit	11

8.3.2	Preparation for the Site Monitoring Visit	12

8.3.3	Tasks to perform during a Site Monitoring Visit	12

8.3.4	Tasks at Conclusion of the Site Monitoring Visit	15

8.3.5	Tasks to Perform After the Site Monitoring Visits	15

8.3.6	Remote Monitoring Visits	16

8.4	Close-out Visit (COV)	16

8.4.1	Preparation for the Close-Out Visit	17

8.4.2	Tasks to perform during Close-out Visit	17

8.4.3	Tasks at Conclusion of the Close-out Visit	17

8.4.4	Tasks Following the Close-out Visit	18

8.5	Emergency Monitoring Measures during a State of Emergency	18

9. Updates to Plan	19

# Introduction

- The Monitoring Plan (MP) describes the minimum monitoring activities expected of the study team for the “Study Title” Study. It is expected that all study team members adhere to the requirements contained in the approved protocol and its amendment(s). Dr. XXX or sponsor is the sponsor of the study and management. The monitoring activities are outsourced to the Centre for Innovative Medicine (CIM), at the Research Institute of the McGill University Health Center, Montreal, Canada.

- Monitoring will be conducted in accordance with applicable CIM Monitoring Standard Operating Procedures (SOPs), the Declaration of Helsinki, the International Conference for Harmonization (ICH)/Good Clinical Practice (GCP) guideline as it applies to the study, and applicable Canadian regulatory requirements.  Please see Section 3 References.

This document should be referenced and followed in conjunction with the Protocol, Investigator Brochure, CIM Monitoring SOPs, and Guidelines where applicable.

The MP will be reviewed periodically and will be updated or revised as needed with approval from the CIM Director of Operations, and Sponsor/Project Manager. Changes to this plan may be made for a number of reasons including, but not limited to, changes in site management and monitoring expectations, or in CIM Monitoring SOPs regarding monitoring tasks.  The most recent approved version of the MP will take precedence over any previous version.

# Overview of the STUDY PROTOCOL/Registry

- The Sponsor or Sponsor-Investigator Study is conducted in Canada.

- Canadian study sites:

| - Site # | - Institution’s name | - Province | - Investigator |
| --- | --- | --- | --- |

Sample Size: ___ Subjects

Project Total Duration:  Approximately ____ months

- The first Site Initiation Visit (SIV) is expected to be performed in Month Year. The subject enrollment is expected to start Month Year. The scope of this MP therefore includes all monitoring activities pertaining to the Site Initiation Visits (SIV), Site Monitoring Visit (SMV) and Close-Out Visit (COV).

# REFERENCES

| Approved Protocol version | Approved Informed Consent Form version |
| --- | --- |
| Version v.#, dd-mm-yyyy | Version v.#, dd-mm-yyyy (EN) |
|  | Version v.#, dd-mm-yyyy (FR) |

- CIM, RI/MUHC (Monitoring) Working Instructions

- Declaration of Helsinki and TCPS2

- ICH E6: International Conference on Harmonisation (ICH) Requirements for Registration of Pharmaceuticals Harmonised Tripartite Guideline, E6: Guideline for Good Clinical Practice (GCP)- E6(R2) Addendum Step 4 version, 9 November 2016

- Health Canada, Food and Drug Regulations, Part C, Division 5, Drugs for Clinical Trials Involving Human Subjects, (Schedule 1024), May 23, 2006.

# List of ABBREVIATIONS and definitions

| Abbreviations | Definitions |
| --- | --- |
| ARC | Academic Research Centre |
| CIM | Centre for Innovative Medicine |
| COV | Close Out Visit |
| CRA | Clinical Research Associate |
| CRF | Case Report Form |
| ICF | Informed Consent Form |
| ISF | Investigator Study Files |
| MP | Monitoring Plan |
| NTF | Note to File |
| PI | Principal Investigator |
| PM | Project Manager |
| REB | Research Ethics Board |
| SMVR | Site Monitoring Visit Reports |
| SDs | Source Documents |
| SDV | Source Data Verification |
| SIV | Site Initiation Visit |
| SMF | Study Master File |
| SMV | Site Monitoring Visit |
| SOP | Standard Operating Procedure |

# Monitor training

The Sponsor or Sponsor-Investigator is responsible for training CIM/Clinical Research Associate (CRA) on the study specific processes. The CIM is responsible for appointing suitably qualified CRAs. CRAs should have sufficient prior knowledge and experience in clinical research to independently conduct monitoring and Source Data Verification (SDV). CRAs should also possess evidence of GCP training.

Before starting on the study, all CRAs must be trained in the following:

- Study specific training (e.g. protocol, Investigator brochure)

- Study Monitoring Plan

- Electronic Data Capture system/paper Case Report Form (CRF completion, querying and remote monitoring)

- SDV (mandatory for CRAs) highlighting important data points to be verified, the process flow of SDV and the percentage of monitoring required

- Applicable CIM SOPs.

Documentation of the training will be placed in the Study Master File (SMF) with the Sponsor/Sponsor-Investigator or the delegates.

# communication

  - Communication with the Sponsor or Sponsor-Investigator

The CRA communicates with the Sponsor or Sponsor-Investigator and is responsible for keeping the Sponsor or Sponsor-Investigator informed of all study/sites related issues.

Regarding the Monitoring Calendar (MC), the CRA is expected to maintain his/her monitoring schedule in an excel sheet (or equivalent).

  - Communication with the Site

The CRA will be the main contact between the investigational site and the Sponsor or Sponsor-Investigator. The CRA will communicate with study site personnel by telephone, fax, e-mail or in face to face meetings e.g. SIV, SMV or COV.

Email correspondence is an acceptable form of communication with the sites. If there is any significant email correspondence with the sites, the email should be filed in the SMF.

General guidance for email correspondence to sites is:

- Instruct the site to never correspond any subject identifiers via e-mail according to Personal Information Protection and Electronic Documents Act (PIPEDA). If study documents are attached in email, any subject identifiers should be removed from the documents, and the documents should be in .PDF format to avoid any modification.

- Copy (Cc) the appropriate study team members.

- Include details of the author’s role and contact information via the “signature” option

- The Urgent (!) symbol will only be used if a response is truly required within 24hrs.

- In general, use the phone rather than email for urgent issues. For important phone communications with sites and sponsor, a telephone contact log should be generated and filed in the SMF.

- All communication titles in the “Subject” section of the email must specify the study short name, Principal Investigator name, the site number “Site XX” and the objective of the email.

# Monitoring and site management guidelines

  - General

The clinical monitoring and site management procedures will be performed in accordance with CIM Monitoring SOPs and ICH/GCP guidelines as it is applicable to the study. The CRA will review regulatory documents, verify subject Informed Consent Form (ICFs), monitor quality of study data and protocol adherence, perform source data verification, review and update the Investigator Study Files (ISF) and provide continued training of the study procedures and protocol adherence.

Significant, urgent, and/or persistent unresolved issues noted during monitoring visits or during remote monitoring should be communicated without delay to the Sponsor or Sponsor-Investigator. The Sponsor or Sponsor-Investigator should notify the CRA the corrective action plan being implemented to address issues.

Section 8 of this document describes the tasks to be performed prior to and during the various types of site visits, as well as the follow-up activities related to those visits.

All monitoring visit activities will be documented by:

- Written confirmation email

- Signing the Monitoring Visit Log for each calendar day of each visit

- Written follow-up letter/email

- Written Visit Report associated with the specific visit (all visit templates are in section 10. Attachments)

  - Monitoring Visit Frequency

The following visits are planned per sites:

- (Wed-based) or (On-Site) Site Initiation Visit (one visit per site)

- Site Monitoring Visit (frequency of visits per site)

- Close-out Visit (one visit per site).

First SMV: After # subjects/site enrolled in the study

Subsequent SMVs:  Number of visits per site until YYYY

Based on the number of the subjects enrolled at each sites, the frequency of the visits and number of visit days may vary.

In addition, if there are study protocol non-compliance issues or there is a significant change in the study staff which requires training of the study staff, an interim SMV can be exceptionally scheduled with the agreement of the Sponsor or Sponsor-Investigator.

  - Site Personnel Training

All site study staff members including (but not limited to) the Principal Investigator, Co-investigators and the Study Nurse/Coordinator will receive training on the study protocol and procedures during the SIV.  If the need for retraining is identified, the CRA will ensure that training is provided.

All subsequent new study staff members will receive training from their study team members who have been initially trained by the Sponsor or Sponsor-Investigator or from the assigned CRA. Every study site related training will be documented on a Training Log (see attachments or ISF) and documented in the MV report, if applicable.

The need for retraining will be assessed at each visit or between the visits and re-training, if required, will be provided online by the CRA or Sponsor/Sponsor-Investigator.

  - Site Visit Reports

CRAs will use the CIM SIV, SMV and COV Report templates for site visits (see attachments).  All draft visit reports and/or draft follow up letters will be submitted for review to the Project Manager (PM) within 10 business days of the visit or last day on site if the visit spans more than one day.  The only report to be submitted to the Study PI for review is the SIV, as the PM is performing that specific Visit for this study. The PM will review visit reports and follow up letter for consistency, completeness and action items within 10 business days and address any issues raised in the reports with the CRA.  All visit reports will then be finalized and signed within 20 business days of the visit and filed in the CIM Study Master File with a copy sent to the Sponsor-Investigator. The follow up letter should be sent to the site after the final visit report is signed, which means within 20 business days after the Monitoring Visit.

*** Please note: If there is no PM involved in the day to day management of the study, then the Sponsor or Sponsor-Investigator will be the Reviewer of these Monitoring Reports.

# Site Visit

As mentioned in Section 7.2 Monitoring Visit Frequency, there is one on site SIV (or web-based) and one Close out visit at each site. The SMVs will be performed at each site, and the visit frequency will be based on the number of subjects excepted per site and the complexity of the study; however, the number of SMVs varies at each site depending on the number of actual subjects enrolled.  This section will describe the types of Site Visits and detail what is to be done pre-visit, during the visit and post-visit.

  - Site Initiation Visits (SIV)

The web-based or on-site SIV will be scheduled and performed once the following study has been approved by the REB and Health Canada (if applicable) and when all documents/materials have been received and filed by the PM/CRA in the SMF:

- Local Institutional Review Board (IRB)/Research Ethics Board (REB) approval for protocol, Investigator’s Brochure, Product Monograph, the ICF, questionnaire, or any other required documents;

- All site specific regulatory documents (e.g. CVs, medical licenses, laboratory normal values, laboratory accreditation, REB submissions, acknowledgements and approvals); Fully signed Clinical Trial Agreement by the Investigator

- No Objection Letter by Health Canada for the protocol, IB, Product monograph, ICF, questionnaire or any other required study documents, if applicable.

The purpose of the SIV is to complete the site preparation for the study. Subject screening activities may not start until this process has been completed.

The SIV training will be given by the CRA or PM to the site study team which includes the Principal Investigator (PI), Co-Investigators, Study Nurse/Coordinator, and other study personnel who will be working on the study.

  - During this presentation, the site personnel will be trained on the protocol any other items that need to be discussed for the conduct of the study. SOP-MO002-05: Site Initiation Visit outlines monitoring procedures for the SIV.

  - Scheduling Site Initiation Visit

The CRA will organize the web-based or on-site Site Initiation Visit (SIV). Once the date and time has been established the CRA will email the site to confirm the SIV and provide an overview and expectations of the presentation.

    - Tasks to be performed during the Site Initiation Visit

The CRA, or designate, will review with the site personnel:

- Protocol requirements/procedures including inclusion/exclusion criteria

- Biological sample processing and collection

- Tour of Pharmacy or where the investigational product (IP) or medical devices are stored:

  - IP/medical device accountability, storage, disposal and return process

- Subject informed consent process

- Source document verification process

- Data collection procedures (Electronic or Paper Case Report Form (CRF) and the CRF completion guidelines)

- Safety reporting process.

The CRA will also review:

- Good Clinical Practices; including investigator’s and sponsor’s responsibilities (if a Sponsor-Investigator Study)

- Responsibilities of site in correspondence and notifications to ethics committees

- Subject confidentiality

- Investigator Study Files: regulatory and study document completion and filing

- Equipment used for the study

- Site correspondence with Sponsor or Sponsor-Investigator and CRA

- Facilities needed for the visit (monitoring room, internet/ computer access, photocopier)

A training log will be completed to summarize all training performed at the SIV.

The Task Delegation Log is completed at or prior to the SIV and kept updated throughout the study. Updated logs should be collected by the CRA at site visits or can be sent by the study team via email to the CRA or PM.

    - Summarizing the Site Initiation Visit

At the close of the visit:

- Address any concerns or questions the site may have

- Review visit findings and any actions required with the Investigator/Study Coordinator.

A copy of the final SIV report will be sent to site for filing in the site’s ISF binder.

  - Site Monitoring Visits

The purpose of Site Monitoring Visits is to proactively facilitate and verify the following:

- The rights, safety and well-being of human subjects are protected by verifying all subjects Informed Consent,

- The conduct of the study is in accordance with applicable regulations, acceptable medical and scientific standards, CIM SOPs, and the protocol,

- Subject recruitment is according to plans,

- The reported study data are accurate, complete and verifiable from source documents by performing quality control review of data:

  - Verify subject information (initials, visit date, etc.) for consistency with available study information

  - Ensure all applicable data fields within the visits are completed, accurate and verifiable from source documents.

    - Scheduling the Site Monitoring Visit

The CRA will be the primary contact for his/her assigned sites. The CRA should schedule the monitoring visit with the site at least 2 to 3 weeks before the visit in order to provide sufficient time to the Study Coordinator and Investigator to be available for the visit.

Once the monitoring visit date has been scheduled, the CRA will send a confirmation email to the Principal Investigator and the Study Coordinator; see attachments for the confirmation email template. The content of the confirmation email should include the following:

- The study name and site to be monitored

- The date and time of the visit*

- The duration of the visit

- A detailed agenda of the items that will be reviewed by the CRA during the course of the visit:

  - A list of unresolved action items from the previous visit, if applicable

  - The lists of documents to be retrieved

  - The name of the person conducting the monitoring visit

  - The name of the study personnel (e.g. PI and SC) who should be available to assist with the visit

  - Which subject consents will be reviewed

  - Which subject medical records hospital charts will be needed, if applicable

  - If the ISF will be reviewed and if any particular documents require attention

  - Monitor’s access to subjects’ medical chart (electronic and/or paper copy)

  - IP/medical device accountability, storage and dispensing, if applicable.

*If the scheduled monitoring visit should change, a new/revised confirmation email must be sent to the site personnel to confirm the changes.

    - Preparation for the Site Monitoring Visit

Once the monitoring visit date has been scheduled and confirmed the CRA will initiate the visit preparation.

To prepare for the monitoring visit, the CRA will:

- Prepare a list of all outstanding issues

- Have a list of Study Documents to be prepared/obtained or retrieved by the site

- Identify the missing study documents to be filed in the site ISF including copies of all communications with the site (e.g. MV confirmation emails, Follow-Up letters, significant emails to or from sites, telephone contact logs, NTFs, etc.). If a call is performed instead of a visit, a telephone contact log should be sent to the site for filing in the ISF.

    - Tasks to perform during a Site Monitoring Visit

During the monitoring visit, the CRA should perform the following:

- 100% SDV of all ICFs

- 100% SDV of all subjects’ inclusion & exclusion criteria, concomitant medications, adverse events and serious adverse events, IP/medical device accountability.

  - The percentage of SDV for the remaining data should have been agreed upon prior to the monitoring visit between the sponsor/sponsor-investigator and CIM

- Follow-up on items from the previous visit, if applicable

- Verify that the Investigator and staff are performing the study procedures in accordance with the protocol, and in agreement between Sponsor/Sponsor-Investigator and the Investigator/Institution

- Review continued adequacy of facilities and staff assignments at site

- Verify that all new study staff have been appropriately trained and all study related trainings were documented with the appropriate training record forms

- Provide any new information regarding a new protocol amendment or update of study processes

- Review and update the site’s ISF (when necessary)

- Address protocol and study process questions

- Sign the Monitoring Log (by CRA and study staff).

Informed Consent Verification:

All ICF forms will be 100% SDV once all subjects are enrolled in the study.  This will include verifying:

- Subject identification and existence as compared to medical records and Subject Identification Log, for all study participants

- Correct completion of the CRF and

- Informed Consent process documentation.

All ICF issues and discrepancies detected during verification will be recorded in the monitoring report.

#### Investigator Study Files Review:

The ISF will be reviewed as needed by the CRA.

The CRA will:

- Review if all study files, are acceptable and placed in a secured location.

- Review all sections and add updated versions of documents.

- Ensure that all essential documents are maintained in the ISF according to the MUHC/RI SOP-CR-15, Investigator Study Files and Essential Documents Reconcile the essential documents and ensure all the regulatory documents are provided to site for filing.

#### Source Document Verification (SDV)

The CRA will review the data entered on the CRF against subject’s source documents. Source documents are considered to be documents that record Subject’s study activities, consultations or examinations and treatment records.  SDV of subject data includes, but is not limited to the following:

- Subject’s charts (hospital records, clinical and office charts, subject diaries or evaluation checklists)

- Paper Follow up questionnaires

- Physician and nursing notes

- Laboratory and imaging reports

- Consultation notes and letters

- Medication dispensing records.

If the study site utilizes electronic subject records, the CRA will be given access to the electronic source documents (provided in compliance with the site’s policy). If site utilizes both electronic and paper source documents, the CRA should have access to both sources, during the monitoring visit.

#### Data Query Resolution

During the monitoring visit, the CRA will post the queries (on the EDC System or on a Data Clarification Form) and make efforts to have them resolved by the site study coordinator on site.  All remaining data queries should be resolved by the site within 2 weeks of the monitoring visit date.

#### Protocol Deviations

A protocol deviation is any instance(s) of failure to follow, intentionally or unintentionally, the requirements of the protocol.

A minor protocol deviation is one that does not affect a subject’s rights, safety and well-being, or the scientific integrity of the clinical investigation. An example of a minor protocol deviation can be but not limited to: failure to comply with the study visit time window.

A major protocol deviation/violation is one that affects a subject’s rights, safety and well-being, or the scientific integrity of the clinical investigation. An example of a major protocol deviation can be but not limited to: inclusion of a subject without their consent, failure to document and report the serious adverse events.

Under emergency circumstances, deviations from the ICF to protect the rights, safety and well-being of human subjects may proceed without prior approval of the Sponsor-Investigator and the IRB/REB.

Every protocol deviation or violation (minor or major) identified will be reported along with an explanation, in the monitoring visit report.  If a deviation or violation is serious then the CRA will notify the Sponsor-Investigator and corrective actions will be taken. The site shall provide a list of these protocol deviations to their IRB/REB, if required by national regulations.

Deviations shall be reported to the Sponsor or Sponsor-Investigator who is responsible for analyzing them and assessing their significance. Deviations should be reviewed to determine the need to amend the protocol or to terminate the investigation.

    - Tasks at Conclusion of the Site Monitoring Visit

The CRA will meet with the Principal Investigator and/or study staff to:

  - Summarize for the PI the work accomplished during the monitoring visit.

  - Address any concerns or questions the site may have

  - Review visit findings and any actions required by the Investigator/Study staff

  - Schedule the next visit, if applicable.

The CRA must immediately notify the Sponsor or Sponsor-Investigator of any critical issues identified at the study site, e.g. significant non-compliance to protocol adherence, persistent errors and data discrepancies, suspicion of scientific misconduct or fraud. These issues must be documented appropriately and followed to resolution. Significant issues that affect subject safety or study integrity will be brought to the attention of the Sponsor or Sponsor-Investigator.

    - Tasks to Perform After the Site Monitoring Visits

A draft monitoring visit report and a Follow-up letter should be sent to the PM for review within 10 working days of the monitoring visit which include the following logs, if applicable:

  - Completed ICF verification log (or equivalent) for all subjects reviewed

  - Cumulated Deviation log

  - CRF log

  - List of all documents collected during the SMV.

After the review and the approval of the final monitoring report by the PM or sponsor, the CRA will send the follow-up letter within 20 business days (after the Monitoring Visit was performed) by email to the PI and the Study Coordinator.

The CRA will follow up on all site action items and document their status until resolution.  All monitoring visit correspondence and original document retrieved/obtained during the visit will be filed in the Study Master File.

    - Remote Monitoring Visits

Remote monitoring visits may be performed between the SMVs.  During the remote monitoring, the CRA may review the subject’s data, non-compliance, generate queries and close the queries, follow up with the outstanding items, etc.

  - Close-out Visit (COV)

The Close-Out Visit (COV) will occur before the final database lock.  A study site may only be closed after the following conditions have been met:

- All eCRFs or paper CRFs are completed and other study data have been received by the Sponsor or Sponsor-Investigator study team

- The current status of all ongoing adverse events and Serious Adverse Events are documented

- All outstanding site related issues/actions are resolved

- All outstanding site payments are made

- All notifications are made to IRB/REB, and regulatory authorities, if required

- All essential documents filed in the ISF are complete and up to date

- All Investigator Obligations (e.g., record retention requirements, financial disclosure, final reports to be submitted by investigator, and specific activities defined by Sponsor-Investigator or the protocol) have been agreed to and/or completed.

A COV can also occur when:

- The Sponsor or Sponsor-Investigator suspends or prematurely terminates either a clinical investigation in an individual investigation site or the entire clinical investigation for significant and documented reasons:

  - If suspicion of an unacceptable risk to subjects arises during the clinical investigation, the sponsor will suspend the clinical investigation while the risk is assessed.

  - If an unacceptable risk is confirmed.

  - If monitoring or auditing identifies serious or repeated deviations on the part of an investigator (i.e. no investigator agreement signed, no subject recruited, protocol non-compliance and CRF not completed, Follow-up visits not performed)

  - A study may be terminated prematurely by sponsor due to low enrollment rate, lack of efficacy, unacceptable toxicity, etc.

- Based on one or more criteria such as the above, clinical management may recommend site / study termination.  The decision process, the considerations that led to the decision, and the parties involved will be documented in the study master file.

- A PI wants to definitively remove their site’s participation from the study.

    - Preparation for the Close-Out Visit

Prior to COV, the CRA should verify and confirm that the conditions in section 8.4 Close-Out Visit (COV) are met.

The CRA conducting the COV should send a confirmation letter/email to the site when the date is fixed with a reminder email approximately five days prior to the visit.

The CRA should communicate with the site’s primary contact staff (e.g. Study Coordinator, Investigator) to:

- Discuss the expected Close-Out Visit activities

- Ensure appropriate staff is available to assist with the activities of the visit

- Ensure the following is available at the Close-out visit:

- A letter notifying the IRB/REB that the study has been completed or terminated

- Prepare regulatory documents for final review

- Prepare Investigator Files for final review

- Ensure outstanding action items have been resolved before the visit date

- Schedule meeting with the PI during the close-out visit to discuss the general overview of the site status and continued PI responsibilities concerning the study.

    - Tasks to perform during Close-out Visit

The following requirements must be done by the CRA during the COV:

- Ensure the end date participation of the team on the Task Delegation Log, obtain the PI’s signature

- Investigator files are complete and accurate

- Sign the Monitoring Log and retrieve a copy for the Study Master File and leave the original in the site binders

- Ensure all outstanding action items are resolved

- Ensure that the site has sent the final safety report (if available), final protocol deviation log and the letter of notification of last Follow-up to their IRB/REB.

    - Tasks at Conclusion of the Close-out Visit

At the conclusion of the study, the CRA will meet with the PI to discuss general overview of the site status and continued responsibilities concerning the study. The following topics should be discussed:

- Activities during the visit and the work accomplished during the Close-out Visit

- Answer study related questions the staff or Investigator may have

- Ongoing storage and maintenance of study documents per ICH/GCP/ISO requirements and permanent document storage plan (Archiving)

- Confidentiality

- Follow-up of study related issues, including the eventuality of sponsor’s audits or regulatory agencies’ inspections

- IRB/REB notification of study completion and/or study site closure (if applicable)

- Publication policy

- Record retention policy (25 years’ record retention for Health Canada regulated studies)

- Ensure the PI’s signature is obtained for final documents and site close-out documentation

- Any final activities.

    - Tasks Following the Close-out Visit

Following the COV, the CRA will complete the Close-out Visit Report and follow-up letter via email and send it to the PM or Sponsor for review within 10 business days. Final and signed versions should be available within 20 business days from the COV.

After review and approval, the CRA will send the COV follow-up letter to the site within 20 business days (same procedure as Monitoring Visit).

Should any items outstanding after the COV, the CRA will ensure that all the items are addressed and resolved and send the final post COV follow up letter to the site.

  - Emergency Monitoring Measures during a State of Emergency

During a state of emergency, the monitor will continue to be the contact person between the research sites and the Sponsor or Sponsor-Investigator. The monitor will also follow up remotely (by e-mail or telephone) with the site regarding any outstanding issues or new issues that may arise during this critical time.

Monitoring activities may need to be re-assessed and should prioritize critical activities to ensure participant safety and data credibility/validity.  Remote monitoring may have to be conducted in lieu of onsite monitoring (if study allows). An electronic alternative may also have to be considered in place of a wet ink signature.

The monitor may review the participant’s data: including safety data, non-compliance, etc. If studies use Electronic Data Capture System (EDC) then the monitor may review this data and may generate manual queries and follow-up for closure of these queries.

If the study is considered critical and recruitment and follow-up is ongoing, the monitor may ask the site to make sure identifying information be redacted on source documents before being shared for remote review. This process must be REB approved and that appropriate measures for exchanging the information be secured prior to sharing during the publicly declared state of emergency.

The monitor will also continue to send monitoring letters describing the remote monitoring performed.  The QI/PI should continue to have oversight and acknowledge review of these monitoring letters (e.g. via email).  All correspondence should be printed and placed in the ISF once the state of emergency has been lifted.

# 9. Updates to Plan

The Monitoring Plan will be reviewed periodically and will be updated and revised as needed. The most recently approved version of the Monitoring Plan will take precedence over any other version.